## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Green
SHARE A MEAL
BY GALIWANGO CHARLES JOVANS
S19B23/119
Project start date: | 2022-11-10 | [10 empty] | Scrolling increment: | [5 empty] | 0
Milestone marker: | 1 | 1 |  |  | November | [20 empty] | December
 | time axis 2022-11-10 to 2023-01-04
Milestone description | Assigned to | Progress | Start | Days | time axis 2022-11-10 to 2023-01-04
IDEATION | Jovans
WRITE UP |  | 100% | 2022-11-10 | 1 | bar: 2022-11-10
PROBLEM STATEMENT |  | 100% | 2022-11-10 | 1 | bar: 2022-11-10
Solution |  | 100% | 2022-11-10 | 3
Defining the Software Process
Software development lifecycle |  | 80% | 2022-11-11 | 1 | bar: 2022-11-11
Definig The Methodology |  | 90% | 2022-11-11 | 2
Planning and Budgeting
Laying out different plans for execution |  | 30% | 2022-11-15 | 3
Listing and calculating out the budget |  | 40% | 2022-11-16 | 5
Modelling and Designing
Visualization of the System |  | 50% | 2022-11-17 | 1 | bar: 2022-11-17
Simulation of the System |  | 40% | 2022-11-17 | 6
Models |  | 30% | 2022-11-20 | 5
Executing the Project Plan
Laying out the different basic features |  | 40% | 2022-11-24 | 1 | bar: 2022-11-24
Splitting them into several modules |  | 20% | 2022-11-24 | 3
1
Development OF The Custmer App
Listing which functionalities to start with |  | 10% | 2022-11-26 | 1 | bar: 2022-11-26
Registration and Login Page |  | 60% | 2022-11-27 | 5
Integerating Google Maps API |  | 0% | 2022-11-30 | 4
Adding Restaurants to the App |  | 0% | 2022-12-03 | 3
Food Items and Menus |  | 0% | 2022-12-03 | 5
Search Filtration |  | 0% | 2022-12-06 | 3
Payment gateway Integration |  | 0% | 2022-12-09 | 4
Real Time Tracking |  | 0% | 2022-12-12 | 3
Delivery options |  | 0% | 2022-12-15 | 7
Push Notifications |  | 0% | 2022-12-21 | 3